## Sheet1
System Name | Shoe Inventory Management
Members: | Rommel John L. Pobadora
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assigned | Date Started | Date Finished | Status | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. USER Managerment | Rommel John Pobadora
1.1. Creating UI | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.2. HomePage | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.3 Register Page | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.4 Login Page/Logout | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.5 Database | Rommel John Pobadora | 2024-10-13 | 2024-10-13 | Done
2. Inventory Management
2.1 Add Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.2 Add Details of the Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.3 Update Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.4 Read Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.5 Update Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.6 Delete Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
3. Sales Management
3.1 Record Sales | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.2 Add Sales | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.3 Quanity sold | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.4 Total Amount Sales | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.5 Update stock | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
4. Product Categorization
4.1 Category | Rommel John Pobadora | 2024-10-28 |  | In Progress
4.2 Sorting | Rommel John Pobadora | 2024-10-28 |  | In Progress
5. Product Search and Filtering
5.1 Search Bar | Rommel John Pobadora | 2024-10-28 | 2024-10-27 | Done
5.2 Product Filter | Rommel John Pobadora | 2024-10-28 |  | In Progress
6. Dashboard Overview
6.1 Simple Dashboard | Rommel John Pobadora | 2024-11-15 |  | Not Started
6.2 Total Dashboard | Rommel John Pobadora | 2024-11-15 |  | Not Started
6.3 Top - Selling Dashboard | Rommel John Pobadora | 2024-11-15 |  | Not Started
6.4 Low Stock Dashboard | Rommel John Pobadora | 2024-11-15 |  | Not Started