## Sheet1
System Name | Shoe Inventory Management
Members: | Rommel John L. Pobadora
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assigned | Date Started | Date Finished | Status | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. USER Managerment | Rommel John Pobadora
1.1. Creating UI | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.2. HomePage | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.3 Register/Login Page with Logout | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.4 Login Page/Logout | Rommel John Pobadora | 2024-09-27 | 2024-10-13 | Done
1.5 Admin Page | Rommel John Pobadora | 2024-10-18 | 2024-11-28 | Done
2. Inventory Management
2.1 Add Shoe (ADMIN) | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.2 Read Shoe | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.3 Update Shoe(ADMIN) | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.4 Delete Shoe (ADMIN) | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
2.6 Inventory UI | Rommel John Pobadora | 2024-10-13 | 2024-10-26 | Done
3. Sales Management
3.1 Record Sales | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.2 Create Sales | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.3 Add Date & Time (PH) | Rommel John Pobadora | 2024-10-25 | 2024-10-27 | Done
3.3 Add Date & Time (PH)
4. Categorization
4.1 Basketball Category | Rommel John Pobadora | 2024-10-28 | 2024-11-18 | Done
4.2 Casual Category | Rommel John Pobadora | 2024-10-28 | 2024-11-18 | Done
4.3 Running Category | Rommel John Pobadora | 2024-10-28 | 2024-11-18 | Done
5. Product Search and Filtering
5.1 Search Bar | Rommel John Pobadora | 2024-10-28 | 2024-10-29 | Done
5.2 Product Filter | Rommel John Pobadora | 2024-10-28 | 2024-10-29 | Done
6. Admin Dashboard Overview
6.1 Top User Sellers | Rommel John Pobadora | 2024-11-15 | 2024-11-26 | Done
6.2 Top Selling Shoes | Rommel John Pobadora | 2024-11-15 | 2024-11-30 | Done
6.3 Lowest Stock Shoes | Rommel John Pobadora | 2024-11-15 | 2024-11-30 | Done